## Sheet1
Item No. | Logged Date | Screen | Items | Actual Result | Expected Result | Reference | Status | Date
MOB001 | 03.09.2015 | Property Enquiry | While pressing back button in Tab | When we press the back button, it shows all the step what the user has done. |  |  | Open
MOB002 |  | Property Enquiry | in all Screens |  | Can Arrage the Semi Colon Symbol. Caption for the headings can be in Capital letters |  | Open
MOB003 |  | Property Enquiry | On Saving Records | Empty Record is Saving |  |  | Open
MOB004 |  | Property Enquiry | while creating a new record | Developer Name is updated with code and developer code is empty in SAP. But in Mobile App when we find the particular record the values is not fetching Correctly |  | Solictior Loc. Is displayed as select | Open
MOB005 |  | Property Enquiry | On Saving Records | Daerah/State value and nageri/Area column values Swapped |  | Have to change the static caption or have to change the binded colums | Open
MOB006 | 04.09.2015 | Property Enquiry | After opening the screen | Unable to find a record |  | When is screen is in add mode the we cant able to find the record | Open
MOB007 |  | Property Enquiry | after adding a record | After clicking the add button the edit button is also is in enabled mode |  |  | Open
MOB008 |  | Property Enquiry | While adding or updating | When we select Dev. Solicitor in mobile app the code is updated in solicitor loc. In SAP the Developer locaiton is empty |  |  | Open
MOB009 |  | Property Enquiry | While viewing a record | When Finding the a record the Solicitor loc is displayed as select |  |  | Open
MOB010 |  | Individual Enquiry | While updating a record | Updating a record is not working |  |  | Open
MOB011 |  | Corporate Enquiry | After opening the Corporate enquiry screen | When pressing the corporate button after giving values in CO. Name column Message like "T&N Noording has stopped" is displayed |  |  | Open